## Blatt1
Task | Person | Task description (as planed) | Start date | End date (as planned) | Activities performed (state dates) | Task (current status) | Completion (in %) | Status (R/Y/G)
WP1.3 | Peter Pan | Perform analyis on multi user tracking technologies for interactive surfaces | 2012-04-25 | 2012-05-09 | 25.04. Identified papers from IEE and ACM (15 papers) 28.04. read all papers 02.05. Reporting about research insights | research perfomed; still need to summarize the findings for the report | 70% | Y
Note on A1: Karsten Nebe: These fields should be filled together with the project leader
Note on F1: Karsten Nebe: This fields are filled by the responsible person